## Slide 1: Agile & Iterative Development
Sungwoon Choi, Ph.D.
Professor, Myongji University
Chair, OMG-Korea
Research Fellow, NIPA
choisw@mju.ac.kr
Agile & Iterative Development. Craig Larman

## Slide 2: Engineering vs. Manufacturing
Manufacturing
  It is possible to first complete specifications, and then build
  Near the start, one can reliably estimate effort and cost
  It is possible to identify, define, schedule, and order all the detailed activities.
  Adaptation to unpredictable change is not the norm, and change-rates are relatively low
Introduction
Engineering/New Product Development
  Rarely possible to create upfront unchanging and detailed specifications
  As empirical data emerge, it becomes increasingly possible to plan and estimate.
  Adaptive steps driven by build-feedback cycles are required.
  Create adaptation to unpredictable change is the norm. Change rates are high.
Engineering
Research
Manufacturing
Assembly
Parts
Product
Requirements
Analysis/Design
Implementation
Predictable
Unpredictable

## Slide 3: Engineering
Introduction
The clients or users are not sure what they want.
They have difficulty stating all they want an know.
As they see the product develop, they change their minds.
External forces (such as a competitor’s product or service) lead to change or enhancements in requires.
The details are overwhelmingly complex for people.
Many details of what they want will only be revealed during development

## Slide 4: Overview
Iterative & Evolutionary
Basic practices of iterative and evolutionary methods, including timeboxing and adaptive planning.
A common mistake adopting iterative methods.
Specific iterative and evolutionary methods, including Evo and UP.

## Slide 5: Iterative Development
Iterative & Evolutionary
An approach to building software (or anything) in which the overall lifecycle is composed of several iterations in sequence.
Each iteration
  Is a self-contained mini-project composed of activities such as requirements analysis, design, programming, and test.
  Produces an iteration release, a stable, integrated and tested partially complete system.
  Includes production-quality programming and management.
Usually the partial system grows incrementally with new features, iteration by iteration
  Incremental development

## Slide 6: Risk-driven and Client-driven Iterative Planning
Introduction
Risk-driven Iterative Development
  Chooses the most risky and difficult elements for the early iterations.
Client-driven Iterative Development
  The choice of features for the next iteration comes from the client-whatever they perceive as the highest business value to them
  The customer adaptively plans the choice for the next iteration, shortly before it starts, based on their latest insight, rather than speculatively at the start of the project.
  The customer has ongoing control and choice, as fresh information arises.
Mixing and ranking iteration goals based the two principles
  Clients do not always appreciate what is technically hard or risky.
  Developers do not always appreciate what has high business values.

## Slide 7: Timeboxed Iterative Development
Introduction
Timeboxing
  Is the practice of fixing the iteration end date and allowing it to change.
If it eventually appears that the chosen requests (the scope) for the iteration can’t be met within the timebox, then
  rather than slip the iteration end date, the scope is reduced (placing lower priority requests back on the wish-list), so that the partial, growing system always ends in stable and tested state on the original planned iteration end date.
Timeboxing should not be used to pressure developers to work longer hours to meet the soon-coming deadline. If the normal pace of work is insufficient, do less
Not all timebox lengths need be equal.
Shorter iteration have lower complexity and risk, better feedback, and higher productivity and success rates.
No changes during the iteration

## Slide 8: Evolutionary and Adaptive Development
Introduction
Evolutionary iterative development
  Implies that the requirements, plan, estimates, and solution evolve or are refined over the course of the iterations, rather than fully defined and frozen in a major up-front specification effort before the development iterations begin.
Adaptive development
  Implies that elements adapt in response to feedback from prior work-feedback from users, test, developers, and so on.
  The intent is the same as evolutionary development, but the name suggests more strongly the feedback-response mechanism in evolution.

## Slide 9: Evolutionary Requirements Analysis
Introduction
In evolutionary and adaptive development, it is not the case that the requirements are forever unbounded or always changing at a high rate.
Rather, most requirements discovery and refinement usually occurs during early iterations, and the earliest attention is given to understanding the most architecturally significant or high-business-value requirements.
Usually after 4 workshops, 90% of the requirements are defined and refined.
Design comments
  It is not true that
    100% of the functional requirements need be known to start building an excellent core architecture. The architect needs to know most nonfuncational or quality requirements and a much smaller representative subset of functional requirements
    Evolutionary process can be proceeded with “no early requirements” or “sloppy requirements”
      It encourages the early creation and baselining of vision statements, “top ten” high level requirements lists, and early analysis of architecturally influential factors.

## Slide 10: Evolutionary and Adaptive Planning
Introduction
Adaptive planning is encouraged rather than predictive planning, because of uncertainty.
The iterative response to this uncertainty is to defer an expectation of semi-reliable estimates for cost, effort or schedule until a few iterations have passed. Perhaps 10% to 20% into a project.
Fixed-Price Contracts
  Run project ts in two contract phases, each of multiple timeboxed iterations.

## Slide 11: Incremental and Evolutionary Delivery
Introduction
The practice of repeatedly delivering a system into production in a series of expanding capabilities.
Incremental deliveries are often between 3 to 12 months.
Incremental delivery contains many iterations.
Evolutionary delivery is a refinement of the practice of incremental delivery in which there is a vigorous attempt to capture feedback regarding the installed product, and use this to guide the next delivery.
To contrast “pure” incremental delivery with evolutionary delivery,
  In incremental delivery, a plan id defined of several future deliveries-feedback is not driving the delivery plan.
  In evolutionary delivery, there is no plan (or at least no fixed plan) of future deliveries; each is dynamically created based on emerging information

## Slide 12: The Most Common Mistakes
Introduction
One of the most common mistake is
  to superimpose big up-front analysis and planning (predictable manufacturing) values onto iterative methods,

## Slide 13: Story
Story of an agile project to relate some practices. This example illustrates a variety of Scrum, XP, Up, and Evo principles and practices
I found that the harder I work, The more luck I seem to have
- Thomas Jefferson -

## Slide 14
Story
It is Monday, January 2. The government Border Information Group (BIG) needs a biometric Recording or Tracking Hazardous External Radicals (BROTHER). BIG has a long list of requests, and Martin, the development manager, has convinced BIG management to use timeboxed iterative development and timeboxed evolutionary delivery. Thus, they will deliver the highest priority features possible by October 1. There is a wish list of features for the first release, and everyone has agreed it may vary, but the release date will not vary.
The plan is that after one or two months in operation at two low-volume airports, feedback from the border guards and travelers will be used to help decide refinements and features for the second release six months later, with a wider rollout.
Following a Scrum practice, Martin and his team of seven developers also commit to demo to the Minister of BIG “running, integrated and tested software every three or four weeks, starting next week.”

## Slide 15
The project will use a combination of practices from Scrum, XP, and UP that Martin and the developers have decided make sense for the team. They organize their physical space: Rather than separate offices or cubicles with dividers, they take over a large room at one of the test airports, FooBarKhan International, near the border guards’ office area. Four cubicles are set up near the project room that people can use when they need private time. The common project room is a Scrum and XP practices.
All furniture against the walls is removed. Tables for computers are placed near the center. The walls are covered in giant white boards, and white board-like static-cling sheets are used as wallpaper elsewhere. This will support the practice of Agile Modeling.
The responsible BIG manager, Domina, moves into the project room, along with Itchy, a long-time border guard. Itchy will be dedicated full0time to the BROTHER project, and Domina agrees to be around “most mornings”. This is the XP practice of onsite clients.

## Slide 16
On Thursday, January 5, they get together and hold a two-day requirements and planning workshop, a UP practices. In addition to receiving a 20-page wish list from senior BIG management, many “ agile requirement analysis” techniques are applied the first morning. After lunch, Martin poses this request: From the high-level requirements we’ve generated, choose the 20% most architecturally significant, risky, and valuable items. They use dot-voting to prioritize the items.
They spend the remaining afternoon and Friday morning analyzing the 20% items in detail. For functional requirements, they apply the UP proactive of writing a few usecases, in the Cockburn style. For the nonfunctional quality requirements, they apply the Evo practice of clearly quantified and measurable goals; the vague “ fast response” and “easy to use” goals in the original BIG wish list were not acceptable.
On Friday after lunch, Martin moves the team on to planning, even though some of the team to spend more time detailing and clarifying specifications. Martin poses this challenge to the group: “We start developing next Monday, January 9. By Thursday, January 26, in 13 working days, we need to have a partial running system hooked up to at least one of the biometric readers. There will be a demo that morning to the BIG minister. What should we realistically do in the next 13 days from the 20% list we explored in detail? And no overtime.” No overtime or “sustainable pace” is an XP practice.

## Slide 17
The group picks a common “happy path” scenario from one of the usecases that will force them to touch on many architectural factors and components (a UP practice), some other features, and spends the afternoon analyzing and estimating the related fine-grained tasks in an XP-style Planning Game. Note that the manager does not create the work breakdown structure, schedule or estimates; the team does this. Eventually, they discover that their first set of goals is too much work, so they scale back some of the features until the estimates match their available Ideal Engineering Hours budget(an XP practice). They wrap the meeting. Martine enters the task items into a Scrum Sprint Backlog spreadsheet.
On Monday, January 9, the first iteration starts.
09:00 They hold a 20-minute daily stand-up Scrum meeting. Martin reminds the tam of the overall vision, and the specific goals of the iteration. They are standing beside the whiteboard where all the iteration tasks are written. After the Scrum questions, team members start volunteering for tasks, writing their name beside them.
Afterwards, the entire group listens to a presentation by Rebecca, the chief architect. Having a chief architect is recommended in UP. Rebecca spend the prior week investigating and considering architectural issues and designs, given the basic information she had. She lays out her vision of the big pieces and problems, to components. Group discussion refines the ideas. Mid-morning, three subgroups head for the walls, doing Agile Modeling for different subcomponents, reviewing the written usecase. The team reserved all of Monday as creative “wall time” to explore and coordinate design ideas during this “fuzzy front end” exploratory phase. Rebecca spends time rotating through all the groups, building a synergy of ideas. Digital snapshots of all the wall notes and UML-ish sketches are taken

## Slide 18
On Tuesday, January 10, teamwork starts at 9:30 with the Scrum meeting. New tasks and impediments are written on the adjacent whiteboard. Martin reminds the team of the vision and iteration goals. More tasks are volunteered for. As previously agreed, they will start programming this morning, even though many design points and coordination issues are fuzzy.
Most of the developers decided they didn’t want to try pair programming, so that XP practice was bypassed, although Martin encouraged pairing by anyone who wanted to try it. However, they all agree to the XP practices of test-driven development and continuous integration. The team is using an IDE with great refactoring tools, and Martin frequently encourages the team to not just cut code, but keep it clean and simple by regularly applying refactorings, another XP practice. The developers occasionally look at the wall sketches or printouts of the snapshots for some inspiration. Some developers head for the walls for 30 minutes to UML-sketch some design ideas, then back to their development stations.
As the day progresses, questions about the features and happy path scenario arise, and Domina and Itchy talk with the developers to clarify and decide the requirements. These two also work with the developer Girija to create acceptance tests-an XP practice.
As developers complete their classes, they check and their unit tests in to the version control server. Girija checks in completed acceptance tests. A separate build machine is running these test within a continuous integration service 24/7. every 15 minutes. Thus, bugs and integration problem are quickly surfaced and resolved. Continuous integration is an XP practice.

## Slide 19
Girija also volunteers to be daily tracker, another XP practice. So each morning, she takes a few minutes to sit with each developer to learn the remaining estimate of effort on their tasks. She updates the Scrum Sprint Backlog spreadsheet with these estimates, and crosses out completed tasks on the white board.
The first few days are rough and confusing. But, by being forced early to develop a very small amount of code and integrate it with the other developers coordination emerges and a small seed of the overall system starts to take shape and be integrated. Hour by hour, more unit and acceptance tests and production code are added to the build.
Fast forward to mid-iteration, Wednesday January 18. The team meets in a sanity check to discuss if they can really meet their original goals by the end of the following Wednesday (in preparation of the Thursday morning demo), or if they need to scale back. Following the timeboxing practices of UP, XP and Scrum, they won’t extend the deadline or work longer hours to meet the deadline, but may defer work until a future iteration. However, things have gone well and the Print Backlog shows the total remaining effort estimate is within budget. So, no changes.

## Slide 20
Next week on Thursday morning, January 26, the BIG minister shows up for the end-of-iteration demo, a Scrum practice. The iris scan demo doesn’t do very much, but it runs and doesn’t crash. The minister has never seen an iterative project before and is impressed that three weeks into a new project, the team has some software to show. She’s used to waiting six months. In addition to encouraging the team with future efforts, the minister shares this: I just attended a cabinet meeting where the Prime Minister enthused about a TV report she saw on automated face recognition in crowds, being used in Grepland. She saw on automated face recognition in crowds, being used in Grepland. She wants it. As soon as possible! This is a matter of national pride; we FooBarKhans can’t be outdone by the Greplanders!
Thursday afternoon and Friday are reserved for a second requirements workshop and iteration 2 planning session. Multiple requirements workshops across early iterations is a UP practice. Since the team is applying the Evo, Scrum, and XP practice of adaptive planning, they had not previously decided what to do in iteration 2, although they had some likely ideas based on the iteration 1 planning session. Rather, they deferred the decision until this time, using their latest information to decide what would be most valuable. With the unexpected overhead and novelty of buying, learning, and integrating a third party face recognition system, the team decides the next iteration needs more slacks and should be four weeks rather than three. The team is very clear what should happen at the iteration 2 demo.

## Slide 21: Process Meta-Model
Activity
  A tangible unit of work performed by a role in a workflow that yields a well-defined result based on a well-defined input.
Work-Product
  A tangible piece of information that is created, changed, and used by roles when performing activities and represents an area of responsibility. A work-product can be a model, model-element, or a document.
Role
  A position that can be assigned to a person or a team, requiring responsibilities and abilities such as performing certain activities and developing certain work-product.
IsResponsibleFor
Activity
Performs
Produces
Uses
0..*
+input
+output
Customer
Work-Product
0..*
1
1
Delivered
Role
0..*
0..*
1
1
1..*
1..*
Resource
Meets
1..*
1..*
Constraint
Respects
1..*
Mission
Requires
1..*
Defines
1..*
1..*

## Slide 22: Motivation
The facts of change on software projects.
Key reasons to adopt iterative and agile development.
Meeting the requirements challenge iteratively.
Problems with the waterfall.
If you are going through hell, keep going
- Sir Winston Churchill -

## Slide 23: If it ain’t broke, don’t fix it
Motivation
If your organization is applying a waterfall-oriented (or any other) process and high success rates, productivity, and so forth, don’t change. Adopting an iterative or agile method should be motivated by a challenge, not method-du-jour fads.
Failure has several meanings.
  For example, late schedule, over budget, wrong product

## Slide 24: The facts of change on software projects
Motivation
The uncertainty principle in software [ZR97]: Uncertainty is inherent and inevitable in software projects and processes.
Jones97 illustrates that software development is a domain of inventive high-change projects
  Boehm and Papaccio also shows that a typical software project experienced a 25% change in requirements [BP88]
  X axis: project size in function points
  Y axis: requirement change rates in percentage
Chart: 
| 10 | 100 | 1000 | 1000
Rates of Change | 1 | 7 | 18 | 33

## Slide 25: Key Motivations for Iterative Development
Motivation
Iterative development is lower risk
Early risk mitigation and discovery
  Risk-driven iterative development forces tackling the hardest, riskiest problems first, such as architecture, integration, and so on.
  And Early development iterations exercise and reveal the true nature of the team and individual skills, the tools, and third-party software.
  Finally the truth of the risks emerges: Perceived risks prove not to be, and unsuspected issues are forced into open
Accommodates and provokes early change; consistent with new product development
Manageable complexity
  Iterative development decomposes complex projects or phases into small and bounded mini-projects of manageable complexity
Confidence and satisfaction from early, repeated success
Early partial product
  Increase client confidence
Relevant progress tracking; better predictability
Higher quality; less defects
Final product better matches true client desires
Early and regular process improvement
Communication and engagement required
IKIWISI(I’ll Know It, When I See It) required

## Slide 26: Timeboxing Benefits
Motivation
Increased Productivity
  Focus: Psychological focus promoted by a fixed end date
    Parkinson’s law: “Work expands so as to fill the time available for its completion” [Parkinson58]
  People remember the slipped dates, not slipped features
    Delay a project 3 months to include 100% of the desired feature set will be remembered as failure
    Deliver with 75% of the most important features on time, is a success.
  The team tackle on manageable complexity
    Research show that lower-complexity steps are done more productively
  The team has to be very realistic about what gets done and what gets deferred
    Since the demo to the client is definitely in the iteration.

## Slide 27: Meeting the requirements challenge iteratively
Motivation
Some interesting statistics
  In a study of over 8,000 projects [Standish94], 37% of the factors on challenged projects were related to requirements
  A study of defects by category [SKTYBE92] found that the largest category was in requirements – 41%
  Boehm [BP88] showed that the cost of fixing a requirement defect increased non-linearly from early to late in the project
  Requirements change 25% or more pJones97, BP88]
  Johnson[Johnson02] showed that 45% of features were not used-with an additional 19% rarely used
Chart: 
| Poor User | Incomplete requirements | Changing Requireemtns | Poor Techincal Skills | Poor Staffing | Others
Factors on challedged proejcts | 13 | 12 | 12 | 7 | 6 | 50
Chart: 
| Always | Often | Sometimes | Rarely | Never
Actual use of requested featues | 7 | 13 | 16 | 19 | 45

## Slide 28: Problems with the Waterfall
Motivation
A waterfall lifecycle pushes many high-risk and difficult elements toward the end of a project,
While Iterative-Incremental Development methods, run by risk-driven iterations, surface and resolve the hardest and riskiest elements early.
Chart: 
| Requirements Analysis | Design | Implementation | Itegrate & System Test
Waterfall
Chart: 
| Iteration1 | Iteration2 | Iteration3 | Iteration4
Waterfall
Waterfall Lifecycle
Iterative Incremental Development
Potential
Impact of risks
Being tackled
Potential
Impact of risks
Being tackled

## Slide 29
Other problems with the waterfall and the misapplication of its values on IID projects include the following points:
  Complete up-front specifications with sign-off
  Late integration and test
  Reliable up-front schedules and estimates
    The waterfall has been called a fail-late lifecycle; one can have the illusion of an accurate schedule during the early, easier phases. This is because the hard and risky elements like integration and test are pushed towards the end.
    It is like the story of the guy who fell off the cliff:
      As he was hurtling down, someone yelled, “How are you doing?” The guy replied, “So far, so good!”
  “Plan the work, work the plan” values
    The maxim is associated with the values of waterfall development, predictive planning, command-control management, up-front specifications and schedules, and so forth.
    This is inconsistent with the agile method principles of adaptive planning, self-organizing and self-directed teams, and evolutionary development

## Slide 30: Evidence
Research, historical, and other evidence related to IID.
Evidence of waterfall risks.
Business case for skills transfer to adopt IID.
Q: What are the most exciting, promising software engineering ideas or techniques on the horizon?
A: I don’t think that the most promising ideas are on the horizon. They are already here and have been for years, but are not being used properly.
- David L. Parnas -

## Slide 31: Overview
Evidence
Research evidence
  Data shows that iterative and evolutionary development is correlated with lower risk, higher productivity and lower defect rates than waterfall projects.
Early large project evidence
  Major and life-critical system have been developed iteratively rather than using the waterfall. Examples include the USA Space Shuttle flight control software developed in 17 iterations, and the new Canadian air traffic control system.
Standards-body evidence
  In the 1980s the USA Department of Defense promoted a waterfall lifecycle in DOD-STD-2167.
  In 1994, MIL-STD-498 was introduced
Expert thought leader evidence
Business case
  Each year, 23% of projects, averaging $1.1 million USD, fail. A two-year ROI analysis of investing $100,000 in iterative skills transfer could show an NPV(Net Present Value) of $700,000 with IRR(Internal Rate of Return) of 200%
Waterfall problems
Why still waterfall promotion?
  Looks simple

## Slide 32: Agile & Iterative Development
Sungwoon Choi, Ph.D.
Professor, Myongji University
Chair, OMG-Korea
Research Fellow, NIPA
choisw@mju.ac.kr